## 
Open Contract Analysis for the Cadillac Forest Management Unit
as of March 10, 2004
Use Page Down Key to See List of Open Sales
Nbr of
|  | Sale Expiration Status | Sales
|  | Contracts Expired | 31 | [9 empty] | Expiration | Expiration | Expiration | Expiration | Expiration
|  | 30 Days before Expiration | 0 | [9 empty] | <0 | >0 | <31 | >30 | <61
|  | 60 Days before Expiration | 6 | [9 empty] | Expiration
|  | >60 Days before Expiration | 63 | [9 empty] | >60
|  | Total | 100
|  | Contract Summary |  |  | Total | [7 empty] | Sale Number | Acres | Volume | Value | Received | Length(days)
|  | Nbr of Open Contracts |  |  | 100 | [7 empty] | > " " | > 0.00 | >0.00 | >0.00 | >0.00 | >0.00
|  | Acres of Open Contracts |  |  | 7419.3
|  | Open Contacts Cords |  |  | 106143.71
|  | Value of Open Contracts |  |  | 4145990.37
|  | Amount Received to Date |  |  | 1968966.93
|  | Amount Remaining |  |  | 2177023.44
|  | Percentage of Contract Value Received to Date |  |  | 47.49%
|  | Expiration Date Used |  |  | 2004-03-10
|  | Avg Contract Length (Years) |  |  | 2.3696
Open Timber Sale Contracts sorted by Days Before Expiration
|  |  |  | Total | Current |  | Contract | Original | Current | Days |  | Current
| Cont |  |  | Cord | Contract | Amount | Issue | Expiration | Expiration | Before |  | Contract
Sale Number | Seq | Sale Name | Acres | Volume | Value | Received | Date | Date | Date | Expiration | Purchaser Name | Length(days)
630349702 | 3 | BLIND-FILER CEDAR 1 | 2 | 82.75 | 811.52 | 877.89 | 1997-08-16 | 1998-06-30 | 2003-06-30 | -408 | DARRYL SOPER | 2144
630359702 | 2 | BLIND-FILER CEDAR 2 | 2 | 73 | 536.85 | 565.13 | 1998-12-08 | 2000-12-31 | 2003-06-30 | -408 | DARRYL SOPER | 1665
630680101 | 1 | NORTH SALVGE | 7 | 34 | 408 | 40.8 | 2001-08-31 | 2003-09-30 | 2003-09-30 | -316 | TOM BURNS | 760
630700101 | 1 | RED 1 SALVAGE | 9 | 38.8 | 465.6 | 46.56 | 2001-08-31 | 2003-09-30 | 2003-09-30 | -316 | TOM BURNS | 760
631040101 | 1 | MEADOWBROOK MIX | 47 | 898.49 | 42785.83 | 42785.83 | 2002-01-02 | 2003-12-31 | 2003-12-31 | -224 | DOYLE FOREST PRODUCTS | 728
630300001 | 1 | CABINOAK | 143 | 2884.53 | 118475.6 | 73342.03 | 2001-03-21 | 2003-03-31 | 2004-03-31 | -133 | OUTMAN FOREST PRODUCTS | 1106
630520101 | 1 | DOUBLE ARROW JACK PINE | 54 | 547.7 | 15643.9 | 1564.39 | 2002-03-25 | 2004-03-31 | 2004-03-31 | -133 | LEON CORLEW | 737
630960101 | 1 | GLADWIN HARDWOODS | 54 | 421.1 | 10600.2 | 10600.2 | 2002-02-20 | 2004-03-31 | 2004-03-31 | -133 | DOYLE FOREST PRODUCTS | 770
630220101 | 1 | HAM ASPEN | 94.3 | 1771 | 78531.96 | 7853.2 | 2002-03-21 | 2004-03-31 | 2004-03-31 | -133 | F.J. FLEES | 741
630330101 | 1 | HORSE TROUGH OAK | 142 | 1735.7 | 53356.19 | 45352.77 | 2002-02-12 | 2004-03-31 | 2004-03-31 | -133 | DAN BUNDY LOGGING INC. | 778
630160101 | 1 | OILFIELD REMOVAL | 54 | 669.8 | 10121.9 | 10121.9 | 2002-02-12 | 2004-03-31 | 2004-03-31 | -133 | SAPPI/WARREN | 778
631020101 | 1 | RAINMAN'S ACCESS | 18 | 186.09 | 14701.63 | 14701.63 | 2002-02-26 | 2004-03-31 | 2004-03-31 | -133 | TONY HYDROLAKE LEASING & SERVICE | 764
630300101 | 1 | ROLLING RED | 199 | 2029.5 | 55520.53 | 23318.63 | 2002-02-08 | 2004-03-31 | 2004-03-31 | -133 | ROBERT GENTZ FOREST PRODUCTS | 782
630600001 | 1 | SMITH'S SUPRISE | 34 | 631.7 | 11541.27 | 11541.27 | 2001-06-11 | 2003-06-30 | 2004-03-31 | -133 | WILFRED EMOND | 1024
631100101 | 1 | SPLIT RAIL TRESPASS | 56.6 | 688.4 | 30630.12 | 3063.01 | 2002-05-10 | 2004-03-31 | 2004-03-31 | -133 | DOYLE FOREST PRODUCTS | 691
630489901 | 1 | STRATFORD OAK | 297 | 1897.13 | 25377.75 | 13574.15 | 2000-03-07 | 2002-03-31 | 2004-03-31 | -133 | MYERS LOGGING | 1485
630120101 | 1 | STRATFORD RED PINE | 42 | 594.5 | 36596.75 | 36596.75 | 2002-03-22 | 2004-03-31 | 2004-03-31 | -133 | BISBALLE FOREST PRODUCTS | 740
630130101 | 1 | STRATFORD WHITE | 42 | 754.3 | 21021.1 | 2102.11 | 2002-03-25 | 2004-03-31 | 2004-03-31 | -133 | LEON CORLEW | 737
630420101 | 1 | SUGAR BOWL HARDWOODS | 210 | 4396.91 | 231879.36 | 231879.36 | 2002-02-20 | 2004-03-31 | 2004-03-31 | -133 | DOYLE FOREST PRODUCTS | 770
630820101 | 1 | WILLY-NILLY HARDWOODS | 83 | 831.66 | 28092.3 | 28092.3 | 2002-05-07 | 2004-03-31 | 2004-03-31 | -133 | NORTHWEST HARDWOODS | 694
631070101 | 1 | WOODCUTTER'S TRAIL | 15 | 446.62 | 17609.4 | 17609.4 | 2002-02-20 | 2004-03-31 | 2004-03-31 | -133 | DOYLE FOREST PRODUCTS | 770
630250201 | 1 | 23 ROAD MIX | 26 | 274.5 | 11380.64 | 1138.06 | 2002-08-02 | 2004-06-30 | 2004-06-30 | -42 | BRUCE BUNDY | 698
630450101 | 1 | BLUE TICK ASPEN | 74.5 | 1851.4 | 63231.15 | 9033.02 | 2001-07-18 | 2003-06-30 | 2004-06-30 | -42 | F.J. FLEES | 1078
630520001 | 1 | BOBCAT JACK | 91 | 931 | 27729.81 | 19769.1 | 2000-12-26 | 2002-12-31 | 2004-06-30 | -42 | SHAWN MUMA | 1282
630140201 | 1 | EACHWAY RED PINE | 58 | 522.49 | 35260.95 | 3527.1 | 2002-07-12 | 2004-06-30 | 2004-06-30 | -42 | DAN BUNDY LOGGING INC. | 719
630460101 | 1 | HAYMARSH ASPEN | 14 | 285.26 | 9984.87 | 1426.41 | 2001-07-18 | 2003-06-30 | 2004-06-30 | -42 | F.J. FLEES | 1078
630210201 | 1 | MCMOUTH ASPEN | 12 | 371.8 | 13941.56 | 13941.56 | 2002-07-12 | 2004-06-30 | 2004-06-30 | -42 | SAPPI/WARREN | 719
630540101 | 1 | NELSON ASPEN | 32 | 372.3 | 10968.93 | 1566.99 | 2001-07-18 | 2003-06-30 | 2004-06-30 | -42 | F.J. FLEES | 1078
630190201 | 1 | RETRY MIX | 61 | 1044.3 | 32759.37 | 13103.76 | 2002-08-22 | 2004-06-30 | 2004-06-30 | -42 | MID MICHIGAN LOGGING | 678
630200201 | 1 | SOPER JACK | 145 | 1767.4 | 53502.45 | 14980.68 | 2002-08-22 | 2004-06-30 | 2004-06-30 | -42 | MID MICHIGAN LOGGING | 678
630100201 | 1 | TRUFFLE PINE | 29 | 250.5 | 18209.62 | 1820.96 | 2002-07-12 | 2004-06-30 | 2004-06-30 | -42 | BLAKE FOREST PRODUCTS | 719
630709901 | 1 | TIMBER RIDGE OAK | 89 | 681.1 | 15331.24 | 10865.83 | 2001-06-01 | 2003-06-30 | 2004-09-15 | 35 | WHEELER'S WOLF LAKE SAWMILL | 1202
630600101 | 1 | 55-PINE | 47 | 496.16 | 18657.99 | 2665.43 | 2001-10-16 | 2003-09-30 | 2004-09-30 | 50 | BISBALLE FOREST PRODUCTS | 1080
630620101 | 1 | A & R JACKPINE | 59 | 821.22 | 22280.62 | 3182.85 | 2001-10-11 | 2003-09-30 | 2004-09-30 | 50 | NORTHERN TIMBERLANDS | 1085
630630101 | 1 | ASPEN RIDGE | 28 | 570.4 | 20017.2 | 2859.6 | 2001-09-18 | 2003-09-30 | 2004-09-30 | 50 | F.J. FLEES | 1108
630290201 | 1 | BLACKMAIL PINE & OAK | 63 | 964.2 | 30810.44 | 3081.04 | 2002-10-09 | 2004-09-30 | 2004-09-30 | 50 | DOYLE FOREST PRODUCTS | 722
630220201 | 1 | NATURAL JACK | 156 | 2490.5 | 71912.17 | 32227.99 | 2002-10-03 | 2004-09-30 | 2004-09-30 | 50 | MID MICHIGAN LOGGING | 728
630900102 | 1 | BORN AGAIN ASPEN | 36 | 682.37 | 4417.2 | 4417.2 | 2001-12-17 | 2004-12-31 | 2004-12-31 | 142 | PARK, CHRIS | 1110
630890102 | 1 | DEER RUN ASPEN | 12 | 253.38 | 1694.8 | 1694.8 | 2001-12-12 | 2004-12-31 | 2004-12-31 | 142 | PARK, CHRIS | 1115
630510101 | 1 | POWER POLE JP | 45 | 728.8 | 23390.96 | 3343.9 | 2001-10-29 | 2003-12-31 | 2004-12-31 | 142 | LEON CORLEW | 1159
630840101 | 1 | Q-TIP RED PINE | 36 | 325.15 | 22658.66 | 22658.66 | 2001-11-20 | 2003-12-31 | 2004-12-31 | 142 | NORTHERN TIMBERLANDS | 1137
630850101 | 1 | RAVEN TRAIL | 19 | 163.66 | 3666.5 | 523.79 | 2001-12-10 | 2003-12-31 | 2004-12-31 | 142 | MICHAEL DELINE | 1117
630910102 | 1 | WEST BRANCH ASPEN | 70 | 835.51 | 5595.3 | 5595.3 | 2001-12-12 | 2004-12-31 | 2004-12-31 | 142 | PARK, CHRIS | 1115
630390101 | 1 | 123 HARDWOODS | 143 | 1274 | 93450.87 | 89000.83 | 2002-04-19 | 2004-03-31 | 2005-03-31 | 232 | PACKAGING CORP. OF AMERICA | 1077
630030301 | 1 | DUNSMORE SALVAGE | 17 | 42.5 | 765.43 | 76.54 | 2003-01-09 | 2005-03-31 | 2005-03-31 | 232 | GARY DOVE | 812
630010301 | 1 | DYER SALVAGE | 5 | 26 | 391.3 | 391.3 | 2003-01-09 | 2005-03-31 | 2005-03-31 | 232 | GARY DOVE | 812
630400201 | 1 | FIRING RANGE RED | 80 | 758.6 | 41780.64 | 29246.42 | 2003-03-11 | 2005-03-31 | 2005-03-31 | 232 | BIEWER SAWMILL INC | 751
630770101 | 1 | FORGE MIX | 174.3 | 3116 | 161669.76 | 16166.98 | 2002-04-02 | 2005-03-31 | 2005-03-31 | 232 | BISBALLE FOREST PRODUCTS | 1094
630060301 | 1 | GREEN PINE | 122 | 1659.9 | 46990.3 | 21145.64 | 2003-02-26 | 2005-03-31 | 2005-03-31 | 232 | BRUCE BUNDY | 764
630120201 | 1 | HILLCLIMB VARIETY | 144 | 2100.2 | 70920.59 | 7092.06 | 2003-03-26 | 2005-03-31 | 2005-03-31 | 232 | SHAWN MUMA | 736
630210101 | 1 | MOREY EAST ASPEN | 92.7 | 2069 | 81562.1 | 8156.21 | 2002-03-21 | 2005-03-31 | 2005-03-31 | 232 | MID MICHIGAN LOGGING | 1106
630230201 | 1 | RIGHT HOOK ASPEN | 31 | 738.1 | 27651.23 | 2765.12 | 2003-03-26 | 2005-03-31 | 2005-03-31 | 232 | SHAWN MUMA | 736
630340201 | 1 | ROSCO RP | 47 | 341.8 | 16901.35 | 1690.14 | 2003-03-19 | 2005-03-31 | 2005-03-31 | 232 | WILFRED EMOND | 743
630260201 | 1 | SCARLET TANAGER HDWD | 40 | 731.86 | 45000.55 | 45000.55 | 2003-03-20 | 2005-03-31 | 2005-03-31 | 232 | ROTHIG FOREST PRODUCTS, INC. | 742
630300201 | 1 | SIX WHEEL MIX | 155 | 2134.22 | 93524.2 | 70142.95 | 2003-03-27 | 2005-03-31 | 2005-03-31 | 232 | ROBERT GENTZ FOREST PRODUCTS | 735
630020201 | 1 | SPIKE HARDWOODS | 200 | 1974 | 70458.7 | 70458.7 | 2003-03-11 | 2005-03-31 | 2005-03-31 | 232 | SAPPI/WARREN | 751
630380201 | 1 | "17 SOUTH PART" | 142 | 1143 | 49341.6 | 4934.16 | 2003-05-20 | 2005-06-30 | 2005-06-30 | 323 | ROBERT GENTZ FOREST PRODUCTS | 772
630440201 | 1 | COMP 14 HARDWOOD | 97 | 1068.4 | 113570.28 | 79499.19 | 2003-05-20 | 2005-06-30 | 2005-06-30 | 323 | ROBERT GENTZ FOREST PRODUCTS | 772
630170201 | 1 | DEAD HORSE BRIDGE JACK PINE | 56 | 745.81 | 20434.5 | 2043.45 | 2003-07-07 | 2005-06-30 | 2005-06-30 | 323 | SHAWN MUMA | 724
630240201 | 1 | HOPPING HUMMOCKS MIX | 78 | 642 | 18778.25 | 1877.83 | 2003-07-07 | 2005-06-30 | 2005-06-30 | 323 | SHAWN MUMA | 724
630070301 | 1 | JACK CORNERS | 55 | 890.4 | 30699.87 | 30699.87 | 2003-06-26 | 2005-06-30 | 2005-06-30 | 323 | SHAWN MUMA | 735
630430201 | 1 | RED HAND HARDWOOD | 79 | 1354.2 | 63706.31 | 6370.63 | 2003-05-20 | 2005-06-30 | 2005-06-30 | 323 | DOYLE FOREST PRODUCTS | 772
630160201 | 1 | SEVEN POINT ASPEN | 52.4 | 624.6 | 21594.7 | 2159.47 | 2003-07-07 | 2005-06-30 | 2005-06-30 | 323 | SHAWN MUMA | 724
630410201 | 1 | STACKPOLE RED PINE | 32.5 | 294.8 | 10236.5 | 1023.65 | 2003-07-02 | 2005-06-30 | 2005-06-30 | 323 | LEON CORLEW | 729
630240301 | 1 | 7 MILE WP | 27 | 293.6 | 8120.59 | 812.06 | 2003-08-07 | 2005-09-30 | 2005-09-30 | 415 | BRUCE BUNDY | 785
630250301 | 1 | 87 RP PIECES | 74 | 810.3 | 43933.77 | 4393.38 | 2003-08-25 | 2005-09-30 | 2005-09-30 | 415 | BISBALLE FOREST PRODUCTS | 767
630050302 | 1 | CON NORTH PINE | 8 | 145.3 | 6538.5 | 6538.5 | 2003-09-17 | 2005-09-30 | 2005-09-30 | 415 | DAN BUNDY LOGGING INC. | 744
630220301 | 1 | COOMBS ASPEN | 65 | 1205 | 55578.33 | 55578.31 | 2003-08-26 | 2005-09-30 | 2005-09-30 | 415 | SAPPI/WARREN | 766
630150201 | 1 | DUSTY PINE | 29 | 349.7 | 10346.23 | 1034.62 | 2002-10-21 | 2005-09-30 | 2005-09-30 | 415 | NORTHERN TIMBERLANDS | 1075
630160301 | 1 | FALMOUTH MIX | 109 | 1512.96 | 44072.91 | 44072.91 | 2003-07-22 | 2005-09-30 | 2005-09-30 | 415 | SHAWN MUMA | 801
630200301 | 1 | FIFE LK CRK RP | 38 | 485.3 | 27016.65 | 2701.67 | 2003-08-04 | 2005-09-30 | 2005-09-30 | 415 | BISBALLE FOREST PRODUCTS | 788
630260301 | 1 | HI-LO ASPEN | 88 | 1906.8 | 81481.4 | 57036.95 | 2003-08-27 | 2005-09-30 | 2005-09-30 | 415 | SHAWN MUMA | 765
630080301 | 1 | HOLEY SAFE | 40 | 900.35 | 33917.6 | 3391.76 | 2003-09-16 | 2005-09-30 | 2005-09-30 | 415 | MURREY FOREST PRODUCTS, INC. | 745
630420201 | 1 | HUNT CLUB SALE | 183 | 4119 | 101639.5 | 10163.95 | 2003-09-17 | 2005-09-30 | 2005-09-30 | 415 | DOYLE FOREST PRODUCTS | 744
630230301 | 1 | RXB PINE | 85 | 1172.1 | 54053.29 | 5405.33 | 2003-08-07 | 2005-09-30 | 2005-09-30 | 415 | BRUCE BUNDY | 785
630090301 | 1 | SQUIDWARD OAK | 46 | 674.5 | 25111 | 2511.1 | 2003-09-16 | 2005-09-30 | 2005-09-30 | 415 | MURREY FOREST PRODUCTS, INC. | 745
631000102 | 1 | ANT HARDWOODS | 4 | 33 | 448.3 | 448.3 | 2003-10-21 | 2005-12-30 | 2005-12-30 | 506 | CHANEY CREEK CONSTRUCTION | 801
630350201 | 1 | "ALMOST SLIPPED BY" | 125 | 1714.29 | 78449.78 | 7844.98 | 2003-10-17 | 2005-12-31 | 2005-12-31 | 507 | ROTHIG FOREST PRODUCTS, INC. | 806
630450302 | 1 | 6 CEDAR | 2 | 70.8 | 784.1 | 784.1 | 2003-11-03 | 2005-12-31 | 2005-12-31 | 507 | ALGER LANGWORTHY | 789
630150301 | 1 | ADDMORE HARDWOODS | 212 | 1945.2 | 56916.88 | 14229.22 | 2003-12-09 | 2005-12-31 | 2005-12-31 | 507 | BRUCE BUNDY | 753
630350301 | 1 | BEE NIMBLE JACK | 117 | 1499.9 | 43203.47 | 28514.29 | 2003-11-26 | 2005-12-31 | 2005-12-31 | 507 | LUTKE FOREST PRODS, INC. | 766
630410301 | 1 | BRINKS ASPEN | 53 | 975.88 | 38509.33 | 3850.93 | 2004-01-05 | 2005-12-31 | 2005-12-31 | 507 | SHAWN MUMA | 726
630280301 | 1 | EVART MOREL HARDWOOD | 53 | 2031.6 | 93493.74 | 9349.37 | 2003-10-29 | 2005-12-31 | 2005-12-31 | 507 | BILLSBY LUMBER | 794
630400301 | 1 | HOMESTEAD JACK | 37 | 766.9 | 21360.62 | 2136.06 | 2004-01-12 | 2005-12-31 | 2005-12-31 | 507 | LUTKE FOREST PRODS, INC. | 719
630030201 | 1 | JIM DANDY OAK | 165 | 2579.4 | 176916.88 | 176916.88 | 2003-10-24 | 2005-12-31 | 2005-12-31 | 507 | NORTHWEST HARDWOODS | 799
630310301 | 1 | MANY BUG ASPEN | 116 | 2158.9 | 93246.4 | 93246.4 | 2003-12-04 | 2005-12-31 | 2005-12-31 | 507 | SAPPI/WARREN | 758
630390301 | 1 | MUSKEGON JACK | 102 | 1009.8 | 34217.01 | 3421.7 | 2004-01-05 | 2005-12-31 | 2005-12-31 | 507 | LUTKE FOREST PRODS, INC. | 726
630040402 | 1 | NEGOTIATE OAK | 4 | 53 | 732.09 | 732.07 | 2003-12-04 | 2005-12-31 | 2005-12-31 | 507 | DAVID D. HYPES | 758
630380301 | 1 | RED ANT JACK | 86 | 805.1 | 31986.62 | 3198.66 | 2004-01-05 | 2005-12-31 | 2005-12-31 | 507 | LUTKE FOREST PRODS, INC. | 726
630010201 | 1 | RED DOG HARDWOODS | 203 | 2475.4 | 161461.32 | 16146.13 | 2003-12-09 | 2005-12-31 | 2005-12-31 | 507 | NORTHWEST HARDWOODS | 753
630370301 | 1 | ROLLWAYS RED PINE | 54 | 820.3 | 56534.39 | 5653.44 | 2004-01-12 | 2005-12-31 | 2005-12-31 | 507 | LUTKE FOREST PRODS, INC. | 719
630420301 | 1 | SCOUNDRELL ASPEN | 46 | 637.96 | 33549.97 | 3355 | 2004-01-05 | 2005-12-31 | 2005-12-31 | 507 | ROTHIG FOREST PRODUCTS, INC. | 726
630040302 | 1 | WILLIES ASPEN 2 | 64 | 1864.3 | 14975.6 | 4492.68 | 2002-12-10 | 2005-12-31 | 2005-12-31 | 507 | OUTMAN FOREST PRODUCTS | 1117
630500301 | 1 | BEAR BAIT PINE | 33 | 569.2 | 19266.79 | 1926.68 | 2004-02-11 | 2006-03-31 | 2006-03-31 | 597 | BRUCE BUNDY | 779
630510301 | 1 | KNOTABUG ASPEN | 81 | 1537.4 | 61252.64 | 61252.64 | 2004-02-13 | 2006-03-31 | 2006-03-31 | 597 | SAPPI/WARREN | 777
630460201 | 1 | LOST LINE ASPEN | 134 | 2976 | 83664.76 | 83664.76 | 2003-03-26 | 2006-03-31 | 2006-03-31 | 597 | BRUCE BUNDY | 1101
630470301 | 1 | POTHOLE PINE | 68 | 903.9 | 31179.31 | 3117.93 | 2004-02-11 | 2006-03-31 | 2006-03-31 | 597 | BRUCE BUNDY | 779
630490301 | 1 | SEELEY RP 2 | 52 | 555 | 28875.96 | 2887.6 | 2004-03-01 | 2006-03-31 | 2006-03-31 | 597 | LUTKE FOREST PRODS, INC. | 760
630480301 | 1 | SKUNKED JACK PINE | 99 | 1348.6 | 36968.72 | 3696.87 | 2004-03-01 | 2006-03-31 | 2006-03-31 | 597 | WEMPLE FOREST PRODUCTS | 760
630270201 | 1 | DEVIL'S CORNER HDWD | 67 | 1210.5 | 54646.7 | 5464.67 | 2003-05-07 | 2006-06-30 | 2006-06-30 | 688 | MALBURG, RICHARD J. | 1150