## 
Open Contract Analysis for the Gwinn Forest Management Unit
as of June 13, 2012
Use Page Down Key to See List of Open Sales
Nbr of
|  | Sale Expiration Status | Sales
|  | Contracts Expired | 4 | [9 empty] | Expiration | Expiration | Expiration | Expiration | Expiration
|  | 30 Days before Expiration | 2 | [9 empty] | <0 | >0 | <31 | >30 | <61
|  | 60 Days before Expiration | 0 | [9 empty] | Expiration
|  | >60 Days before Expiration | 84 | [9 empty] | >60
|  | Total | 90
|  | Contract Summary |  |  | Total | [7 empty] | Sale Number | Acres | Volume | Value | Received | Length(days)
|  | Nbr of Open Contracts |  |  | 90 | [7 empty] | > " " | > 0.00 | >0.00 | >0.00 | >0.00 | >0.00
|  | Acres of Open Contracts |  |  | 5964.6
|  | Open Contacts Cords |  |  | 80371.34
|  | Value of Open Contracts |  |  | 3740346.18
|  | Amount Received to Date |  |  | 1366286.02
|  | Amount Remaining |  |  | 2374060.16
|  | Percentage of Contract Value Received to Date |  |  | 36.53%
|  | Expiration Date Used |  |  | 2012-06-13
|  | Avg Contract Length (Years) |  |  | 4.0304
Open Timber Sale Contracts sorted by Days Before Expiration
|  |  |  | Total | Current |  | Contract | Original | Current | Days |  | Current
| Cont |  |  | Cord | Contract | Amount | Issue | Expiration | Expiration | Before |  | Contract
Sale Number | Seq | Sale Name | Acres | Volume | Value | Received | Date | Date | Date | Expiration | Purchaser Name | Length(days)
321290801 | 1 | MT. HARLOW SALE | 60.6 | 889.4 | 34742.88 | 3474.29 | 2009-06-24 | 2011-05-31 | 2011-05-31 | -379 | ROBERT MINERICK | 706
320220901 | 1 | EAST CABLES MIX | 87 | 1065.4 | 21023.05 | 30887.64 | 2009-03-20 | 2012-05-31 | 2012-05-31 | -13 | LAFLEUR FOREST PRODUCTS, LLC | 1168
323050801 | 1 | JJ'S GOLD MINE SALE | 48.8 | 437.6 | 14249.97 | 14249.97 | 2009-03-11 | 2011-05-31 | 2012-05-31 | -13 | S.D. WARREN SERVICE COMPANY | 1177
323040601 | 2 | NORTH BOAR'S NEST | 184 | 2571.2 | 49567.59 | 42263.95 | 2007-11-21 | 2011-05-31 | 2012-05-31 | -13 | TRIEST FOREST PRODUCTS INC | 1653
321120701 | 1 | HIGH-LOW SALE | 62 | 1207 | 33639.64 | 33639.64 | 2007-10-31 | 2010-11-30 | 2012-06-30 | 17 | MINERICK LOGGING, INC. | 1704
320160801 | 1 | OLD LANDFILL ASPEN | 123.8 | 1949.3 | 72627.73 | 72627.73 | 2008-11-05 | 2011-11-30 | 2012-06-30 | 17 | KANERVA FOREST PRODUCTS, INC. | 1333
320090901 | 1 | 438 ASPEN | 21 | 430.3 | 13618.4 | 13618.4 | 2009-08-14 | 2012-05-31 | 2012-08-31 | 79 | MINERICK LOGGING, INC. | 1113
320210701 | 1 | BROKEN HATCHET | 36 | 140 | 9128.79 | 9128.79 | 2007-07-18 | 2010-05-31 | 2012-08-31 | 79 | C.J. LOGGING | 1871
320030801 | 1 | 438 SPLIT | 12 | 59.6 | 1983.39 | 1983.39 | 2009-03-26 | 2011-05-30 | 2012-08-31 | 79 | C.J. LOGGING | 1254
320070801 | 1 | TWO COUNTY ASPEN | 70 | 1517.6 | 47941.59 | 4794.16 | 2009-04-01 | 2012-11-30 | 2012-11-30 | 170 | ROBERT MINERICK | 1339
320110901 | 1 | CAMP 10 MIX | 107 | 2352 | 91733.75 | 9173.38 | 2010-04-26 | 2012-11-30 | 2012-11-30 | 170 | MINERICK LOGGING, INC. | 949
320060901 | 1 | RW HARDWOOD | 14 | 213.4 | 5659.85 | 5659.85 | 2009-08-13 | 2012-11-30 | 2012-11-30 | 170 | KANERVA FOREST PRODUCTS, INC. | 1205
320060801 | 1 | BILSKY LAKE ASPEN | 43 | 821.98 | 36805.8 | 36805.8 | 2008-07-21 | 2011-11-30 | 2012-11-30 | 170 | MINERICK LOGGING, INC. | 1593
321010901 | 1 | MARTIN'S LANDING SALE | 29.6 | 510.7 | 16611.63 | 16611.63 | 2010-01-27 | 2012-11-30 | 2012-11-30 | 170 | MINERICK LOGGING, INC. | 1038
321031001 | 1 | CAMP BERGAMO | 37.1 | 596.8 | 25042.33 | 2504.23 | 2010-08-04 | 2012-11-30 | 2012-11-30 | 170 | HOLLI FOREST PRODUCTS, INC. | 849
321041001 | 1 | FLAT ROCK RED PINE | 30 | 160 | 7914.17 | 7914.17 | 2010-08-04 | 2012-11-30 | 2012-11-30 | 170 | HOLLI FOREST PRODUCTS, INC. | 849
321061001 | 1 | CAMP HOPE OAK-BIRCH | 88 | 1528.6 | 69097.93 | 69097.93 | 2010-10-13 | 2012-11-30 | 2012-11-30 | 170 | MINERICK LOGGING, INC. | 779
321071001 | 1 | BROKEN BINDING ASPEN | 90 | 1171 | 37977.27 | 37977.27 | 2010-08-04 | 2012-11-30 | 2012-11-30 | 170 | HOLLI FOREST PRODUCTS, INC. | 849
321111001 | 1 | CRANBERRY LAKE HARDWOOD | 47 | 381.2 | 12597.93 | 1259.79 | 2010-05-03 | 2012-11-30 | 2012-11-30 | 170 | MINERICK LOGGING, INC. | 942
320210801 | 1 | WERNER BRIDGE SALE | 80.7 | 926.7 | 33968.58 | 33968.58 | 2008-11-05 | 2011-11-30 | 2012-11-30 | 170 | KANERVA FOREST PRODUCTS, INC. | 1486
321270801 | 1 | SWEENY SAND SALE | 92 | 1958.96 | 48645.96 | 48645.96 | 2008-01-21 | 2012-11-30 | 2012-11-30 | 170 | HEIDTMAN LOGGING, INC | 1775
320131001 | 1 | TIC ASPEN | 75 | 736 | 31182 | 3118.2 | 2010-11-03 | 2013-05-30 | 2013-05-30 | 351 | K & K LOGGING | 939
321021001 | 1 | THOMAS LAKE HARDWOOD | 123 | 1130.8 | 26653.2 | 2665.32 | 2011-05-12 | 2013-05-31 | 2013-05-31 | 352 | J. CAREY LOGGING INC | 750
320091001 | 1 | ROSS CREEK HARDWOODS | 116 | 855.6 | 40004.44 | 4004.44 | 2010-11-15 | 2013-05-31 | 2013-05-31 | 352 | MINERICK LOGGING, INC. | 928
320081001 | 1 | LIARS LODGE HARDWOODS | 64 | 405.4 | 22273.2 | 2227.32 | 2010-11-19 | 2013-05-31 | 2013-05-31 | 352 | SANVILLE LOGGING, INC. | 924
320071001 | 1 | BRIDGE ONE CAMP | 43 | 814 | 42063.06 | 4206.31 | 2011-06-30 | 2013-05-31 | 2013-05-31 | 352 | ROY NELSON JR & SON FOR. PROD. | 701
320161001 | 1 | HAMILTON ASPEN | 117 | 2135 | 102505.5 | 10250.55 | 2010-07-02 | 2013-05-31 | 2013-05-31 | 352 | MINERICK LOGGING, INC. | 1064
320171001 | 1 | STRETCHS CAMP | 33 | 293 | 10491.23 | 1049.12 | 2011-07-11 | 2013-05-31 | 2013-05-31 | 352 | RALPH BUGAY & SON LOGGING | 690
321260901 | 1 | SAND RIVER BLADE SALE | 175.8 | 3876.4 | 146164.92 | 146164.92 | 2010-04-26 | 2013-05-31 | 2013-05-31 | 352 | HEIDTMAN LOGGING, INC | 1131
323220601 | 1 | KAWBAWGAM SALE | 103.1 | 1370.8 | 50464.25 | 14129.99 | 2007-09-21 | 2010-05-31 | 2013-05-31 | 352 | SANVILLE LOGGING, INC. | 2079
321260701 | 2 | DALTON SALE | 23.1 | 258.6 | 8954 | 8954 | 2007-11-07 | 2010-05-31 | 2013-05-31 | 352 | TRIEST FOREST PRODUCTS INC | 2032
323021001 | 1 | OUT NORTH SALE | 56 | 823 | 32245.82 | 3224.58 | 2011-05-10 | 2013-05-31 | 2013-05-31 | 352 | HOLLI FOREST PRODUCTS, INC. | 752
321020701 | 1 | SAND R. MAPLE SALE | 132.4 | 1944 | 81038.12 | 81038.12 | 2008-04-30 | 2011-05-31 | 2013-05-31 | 352 | ROY NELSON JR & SON FOR. PROD. | 1857
320050901 | 1 | FERGIE HARDWOODS | 100 | 492.5 | 27160.5 | 8148.15 | 2010-05-07 | 2013-05-31 | 2013-05-31 | 352 | RON GRAVES LOGGING | 1120
320041001 | 1 | WHITEYS HILL | 83 | 284.8 | 32494.2 | 3249.42 | 2010-08-03 | 2013-05-31 | 2013-05-31 | 352 | RON GRAVES LOGGING | 1032
320031001 | 1 | CROOKED LAKE ASPEN | 29 | 523 | 21676 | 2167.6 | 1911-02-09 | 1913-05-31 | 2013-05-31 | 352 | LAFLEUR FOREST PRODUCTS, LLC | 37367
321051001 | 1 | CAMP HOPE ROAD ASPEN | 40 | 705 | 29117.2 | 29117.2 | 2010-11-14 | 2013-05-31 | 2013-05-31 | 352 | MINERICK LOGGING, INC. | 929
321151001 | 1 | VOELKER PLAINS JACK PINE-ASPEN | 53 | 276 | 10094.6 | 1009.46 | 2011-02-09 | 2013-05-31 | 2013-05-31 | 352 | LAFLEUR FOREST PRODUCTS, LLC | 842
320021001 | 1 | KENTUCKY GRADE MIX | 18 | 168 | 7112.75 | 711.28 | 2010-11-03 | 2013-05-31 | 2013-05-31 | 352 | K & K LOGGING | 940
320011001 | 1 | SUCKER CREEK MIX | 57 | 808 | 32479.15 | 3247.92 | 2011-09-26 | 2011-11-30 | 2013-10-31 | 505 | ROY NELSON JR & SON FOR. PROD. | 766
320121001 | 1 | KAUPPILA ACCESS HARDWOODS | 27 | 233.2 | 7497.45 | 749.75 | 2010-07-09 | 2013-11-30 | 2013-11-30 | 535 | DIVERSIFIED FORESTRY | 1240
321111101 | 1 | PATCHY JACK SALE | 38.5 | 365 | 14825.9 | 1482.59 | 2011-06-15 | 2013-11-13 | 2013-11-30 | 535 | LAFLEUR FOREST PRODUCTS, LLC | 899
321120901 | 1 | BLUEBERRY PINE SALE | 51.5 | 862 | 50655.76 | 5065.58 | 2011-11-22 | 2013-11-30 | 2013-11-30 | 535 | MINERICK LOGGING, INC. | 739
320011101 | 1 | KAMIKAZE PARTRIDGE | 76 | 1026 | 67253.6 | 6725.36 | 2011-09-13 | 2013-11-30 | 2013-11-30 | 535 | LAFLEUR FOREST PRODUCTS, LLC | 809
321101001 | 1 | BRYAN PINE SALE | 135 | 2313 | 164145.45 | 82072.73 | 2011-04-15 | 2013-11-30 | 2013-11-30 | 535 | MINERICK LOGGING, INC. | 960
321081101 | 1 | FLAT TOP ROCK SALE | 33 | 590 | 26872.29 | 2687.23 | 2012-02-06 | 2013-11-30 | 2013-11-30 | 535 | TRIEST FOREST PRODUCTS INC | 663
320051001 | 1 | BOB WILSON SPRUCE | 55 | 993 | 58645.84 | 5864.58 | 2011-07-08 | 2013-11-30 | 2013-11-30 | 535 | GIGUERE LOGGING, INC | 876
320061001 | 1 | HIGH BANKS HARDWOOD | 17 | 166 | 5798.45 | 579.85 | 2011-07-19 | 2013-11-30 | 2013-11-30 | 535 | MOTTO LOGGING | 865
321131001 | 1 | TRIPLE A WHITE SALE | 137 | 1841 | 74073.14 | 7407.31 | 2011-02-07 | 2013-11-30 | 2013-11-30 | 535 | HOLLI FOREST PRODUCTS, INC. | 1027
321061101 | 1 | FLAT ROCK BIRCH SALE | 47.1 | 931.6 | 47148.54 | 4714.85 | 2011-11-22 | 2013-11-30 | 2013-11-30 | 535 | MINERICK LOGGING, INC. | 739
321041101 | 1 | FLAT ROCK RD. MIX | 26 | 362 | 16043.5 | 1604.35 | 2011-05-18 | 2013-11-30 | 2013-11-30 | 535 | DAVE JOHNSON LOGGING | 927
321031101 | 1 | HEART LAKE SALE | 109 | 1969 | 78776.64 | 7877.66 | 2011-12-14 | 2014-05-30 | 2014-05-30 | 716 | HOLLI FOREST PRODUCTS, INC. | 898
320021201 | 1 | LEISNER ASPEN | 86 | 1348.4 | 68312.28 | 6831.23 | 2012-06-11 | 2014-05-31 | 2014-05-31 | 717 | TRIEST FOREST PRODUCTS INC | 719
320021101 | 1 | IRONCLAD SWAMP BUCK | 66 | 1840 | 111702.94 | 111702.94 | 2011-09-13 | 2014-05-31 | 2014-05-31 | 717 | TRIEST FOREST PRODUCTS INC | 991
323051101 | 1 | HEMMINGS EXTENDED ASPEN | 31 | 666 | 32788.83 | 3278.88 | 2012-04-16 | 2014-05-31 | 2014-05-31 | 717 | MINERICK LOGGING, INC. | 775
320051101 | 1 | KC MIX | 76 | 631.4 | 72976.3 | 7297.63 | 2011-10-04 | 2014-05-31 | 2014-05-31 | 717 | LAFLEUR FOREST PRODUCTS, LLC | 970
323031001 | 1 | VAN RIPER LAKES | 20 | 322.4 | 10509.1 | 1050.91 | 2012-05-24 | 2014-05-31 | 2014-05-31 | 717 | PLUM CREEK MARKETING, INC. | 737
323061101 | 1 | KATE AND CHARLIE | 28 | 400 | 18798.95 | 18798.95 | 2012-04-02 | 2014-05-31 | 2014-05-31 | 717 | K & K LOGGING | 789
323041101 | 1 | DOUBLE CAMERA ASPEN | 35 | 275 | 13610.1 | 1361.01 | 2012-04-10 | 2014-05-31 | 2014-05-31 | 717 | LAFLEUR FOREST PRODUCTS, LLC | 781
321181101 | 1 | K.I.H. SALE | 35 | 383.4 | 12935.92 | 1293.59 | 2012-03-19 | 2014-05-31 | 2014-05-31 | 717 | GAZAN TIMBER CONTRACTING, INC. | 803
321021101 | 1 | ISLAND LAKE ROAD PINE | 34 | 724 | 42229.09 | 4222.91 | 2012-04-10 | 2014-05-31 | 2014-05-31 | 717 | MINERICK LOGGING, INC. | 781
321011101 | 1 | CLOWRY-BURMA SPF | 66 | 1269 | 56649.97 | 5665 | 2012-03-19 | 2014-05-31 | 2014-05-31 | 717 | MINERICK LOGGING, INC. | 803
320151101 | 1 | ASPEN PATCHES PLUS | 37 | 660.6 | 28919.1 | 8675.72 | 2011-01-19 | 2014-05-31 | 2014-05-31 | 717 | K & K LOGGING | 1228
321051101 | 1 | FLAT ROCK PINE ISLANDS | 34 | 577 | 24146.11 | 2414.61 | 2011-12-14 | 2014-05-31 | 2014-05-31 | 717 | HOLLI FOREST PRODUCTS, INC. | 899
321091101 | 1 | VOELKER RED PINE-SPRUCE | 76.5 | 900.4 | 48938.71 | 4893.87 | 2011-12-14 | 2014-05-31 | 2014-05-31 | 717 | HOLLI FOREST PRODUCTS, INC. | 899
320131101 | 1 | SAARIS CAMP | 124 | 772 | 69335.1 | 35360.9 | 2011-11-29 | 2014-05-31 | 2014-05-31 | 717 | K & K LOGGING | 914
321101101 | 1 | HEMMINGS PINE-ASPEN | 88 | 1237 | 90752.39 | 90752.39 | 2012-04-04 | 2014-05-31 | 2014-05-31 | 717 | GIGUERE LOGGING, INC | 787
323031101 | 1 | BBR NORTH | 23 | 369 | 12175.49 | 1217.55 | 2012-03-19 | 2014-11-01 | 2014-11-01 | 871 | MINERICK LOGGING, INC. | 957
321071101 | 1 | FLAT ROCK CONGLOMERATE SALE | 71 | 1279 | 76161.55 | 7616.16 | 2012-04-16 | 2014-11-30 | 2014-11-30 | 900 | MINERICK LOGGING, INC. | 958
321121101 | 1 | CHARLIE CHAIN ASPEN | 84 | 1231 | 70115.68 | 7011.57 | 2012-04-30 | 2014-11-30 | 2014-11-30 | 900 | MINERICK LOGGING, INC. | 944
320031101 | 1 | BLACKED OUT SPRUCE | 28 | 602 | 37263.51 | 3726.35 | 2011-08-09 | 2014-11-30 | 2014-11-30 | 900 | BRIAN CHOLEWA LOGGING | 1209
320061101 | 1 | SESQUICENTENNIAL ASPEN | 30 | 802 | 50204.25 | 5020.43 | 2011-09-06 | 2014-11-30 | 2014-11-30 | 900 | LAFLEUR FOREST PRODUCTS, LLC | 1181
320031201 | 1 | ESCANABA R. CAMPSITE ASPEN | 20 | 299.9 | 12766 | 1276.6 | 2012-05-23 | 2014-11-30 | 2014-11-30 | 900 | LAFLEUR FOREST PRODUCTS, LLC | 921
320111101 | 1 | WAYS ACCESS ASPEN/FIR | 17 | 252 | 9090.45 | 909.05 | 2011-09-08 | 2014-11-30 | 2014-11-30 | 900 | SANVILLE LOGGING, INC. | 1179
320041101 | 1 | SHAMROCK GATE ASPEN | 82 | 1178 | 67945.45 | 6794.55 | 2011-09-13 | 2014-11-30 | 2014-11-30 | 900 | LAFLEUR FOREST PRODUCTS, LLC | 1174
320101101 | 1 | EAST LITTLE WEST | 52 | 545.1 | 30099.8 | 3009.98 | 2011-11-29 | 2014-11-30 | 2014-11-30 | 900 | K & K LOGGING | 1097
320191101 | 1 | JOHNSON BASIN HARDWOODS | 59 | 581.4 | 24806.04 | 2480.6 | 2012-05-08 | 2015-05-31 | 2015-05-31 | 1082 | ROY NELSON JR & SON FOR. PROD. | 1118
321191101 | 1 | SAND RIVER SPLIT SALE | 60 | 456.6 | 24455.65 | 2445.57 | 2012-05-08 | 2015-05-31 | 2015-05-31 | 1082 | ROY NELSON JR & SON FOR. PROD. | 1118
321201101 | 1 | SAND RIVER RUN SALE | 107 | 895.9 | 44968.45 | 4496.85 | 2012-02-06 | 2015-05-31 | 2015-05-31 | 1082 | TRIEST FOREST PRODUCTS INC | 1210
320141001 | 1 | DEADHORSE CREEK HARDWOODS | 177 | 1184.6 | 36531.3 | 15811.06 | 2011-07-12 | 2015-05-31 | 2015-05-31 | 1082 | WILLIAMS SPECIALTY WOODS | 1419
320221101 | 1 | VESSEL CAMP REVISED | 28 | 75 | 2667.9 | 266.79 | 2012-05-23 | 2015-05-31 | 2015-05-31 | 1082 | RON GRAVES LOGGING | 1103
320181101 | 1 | CARLSHEND HARDWOODS | 97 | 435.4 | 29995.5 | 2999.55 | 2012-05-04 | 2015-05-31 | 2015-05-31 | 1082 | GIGUERE LOGGING, INC | 1122
320061201 | 1 | ESCANABA RIVER RD #1 | 61 | 1154 | 60259 | 6025.9 | 2012-05-23 | 2015-05-31 | 2015-05-31 | 1082 | LAFLEUR FOREST PRODUCTS, LLC | 1103
320071101 | 1 | E. 557 PINE BLOCKS | 47 | 743.2 | 59618.2 | 5961.82 | 2011-09-08 | 2015-05-31 | 2015-05-31 | 1082 | GIGUERE LOGGING, INC | 1361
320071201 | 1 | DADS PLACE ASPEN | 23 | 347.5 | 16217.9 | 1621.79 | 2012-05-23 | 2015-05-31 | 2015-05-31 | 1082 | LAFLEUR FOREST PRODUCTS, LLC | 1103
320141101 | 1 | ROUGH RIDERS | 58 | 1354 | 77535.6 | 7753.56 | 2012-01-19 | 2015-05-31 | 2015-05-31 | 1082 | LAFLEUR FOREST PRODUCTS, LLC | 1228
320081101 | 1 | W. 557 PINE BLOCKS | 53 | 597.8 | 47110.8 | 4711.08 | 2011-09-08 | 2015-05-31 | 2015-05-31 | 1082 | GIGUERE LOGGING, INC | 1361
320201101 | 1 | CHAINING ASPEN | 86 | 797 | 44801.11 | 4480.11 | 2012-04-30 | 2015-05-31 | 2015-05-31 | 1082 | MINERICK LOGGING, INC. | 1126
320091101 | 1 | EXCLUSION HARDWOODS | 277 | 2182.4 | 131103.52 | 13110.35 | 2011-10-10 | 2015-05-31 | 2015-05-31 | 1082 | TRIEST FOREST PRODUCTS INC | 1329
320051201 | 1 | ESCANABA RIVER RD #2 | 31 | 561.5 | 21359.21 | 2135.92 | 2012-06-11 | 2015-05-31 | 2015-05-31 | 1082 | MINERICK LOGGING, INC. | 1084