## 
Open Contract Analysis for the Roscommon Forest Management Unit
as of December 8, 2010
Use Page Down Key to See List of Open Sales
Nbr of
|  | Sale Expiration Status | Sales
|  | Contracts Expired | 0 | [9 empty] | Expiration | Expiration | Expiration | Expiration | Expiration
|  | 30 Days before Expiration | 1 | [9 empty] | <0 | >0 | <31 | >30 | <61
|  | 60 Days before Expiration | 0 | [9 empty] | Expiration
|  | >60 Days before Expiration | 62 | [9 empty] | >60
|  | Total | 63
|  | Contract Summary |  |  | Total | [7 empty] | Sale Number | Acres | Volume | Value | Received | Length(days)
|  | Nbr of Open Contracts |  |  | 63 | [7 empty] | > " " | > 0.00 | >0.00 | >0.00 | >0.00 | >0.00
|  | Acres of Open Contracts |  |  | 4284
|  | Open Contacts Cords |  |  | 70454.7
|  | Value of Open Contracts |  |  | 3086684.74
|  | Amount Received to Date |  |  | 1342510.01
|  | Amount Remaining |  |  | 1744174.73
|  | Percentage of Contract Value Received to Date |  |  | 43.49%
|  | Expiration Date Used |  |  | 2010-12-08
|  | Avg Contract Length (Years) |  |  | 2.1751
Open Timber Sale Contracts sorted by Days Before Expiration
|  |  |  | Total | Current |  | Contract | Original | Current | Days |  | Current
| Cont |  |  | Cord | Contract | Amount | Issue | Expiration | Expiration | Before |  | Contract
Sale Number | Seq | Sale Name | Acres | Volume | Value | Received | Date | Date | Date | Expiration | Purchaser Name | Length(days)
710200701 | 1 | AU SABLE ASPEN | 26 | 391.2 | 9348.7 | 9348.7 | 2007-11-19 | 2009-12-31 | 2010-12-31 | 23 | DANKERT WOOD PRODUCTS | 1138
710250801 | 1 | EMERY HILL OAK | 33 | 819.8 | 31841.4 | 3184.14 | 2009-02-03 | 2011-03-31 | 2011-03-31 | 113 | T. R. TIMBER COMPANY | 786
710240801 | 1 | RORSCHACH RED PINE | 38 | 595.4 | 23194.25 | 23194.25 | 2009-02-02 | 2011-03-31 | 2011-03-31 | 113 | THOMAS AKIN | 787
710041101 | 1 | DUCK CLUB OAK | 122 | 1730.2 | 72537.6 | 7253.76 | 2010-11-16 | 2011-04-01 | 2011-04-01 | 114 | SHAWN MUMA LOGGING | 136
710090901 | 1 | MOORSETOWN RED PINE | 20 | 192 | 3476.05 | 347.61 | 2009-05-19 | 2011-06-30 | 2011-06-30 | 204 | OMELL FOREST PRODUCTS | 772
710230601 | 1 | WINTERGREEN OAK | 30 | 266.9 | 5729.07 | 1245.45 | 2007-05-29 | 2009-06-30 | 2011-06-30 | 204 | BISBALLE FOREST PRODUCTS | 1493
710220701 | 1 | A.R.P. BORDER | 18 | 204 | 3951.99 | 3951.99 | 2008-04-30 | 2010-06-30 | 2011-06-30 | 204 | DANKERT WOOD PRODUCTS | 1156
710110801 | 1 | ROLLWAY RED PINE | 71 | 798.2 | 41645.72 | 20822.87 | 2009-06-02 | 2011-06-30 | 2011-06-30 | 204 | HYDROLAKE, INC. | 758
710530801 | 1 | STONEY RIDGE OAK | 140 | 1719.4 | 73595.19 | 73595.2 | 2009-06-02 | 2011-06-30 | 2011-06-30 | 204 | LEONARD FOREST PRODUCTS, INC. | 758
710330801 | 1 | REILLY ROAD OAK | 97 | 1382 | 41204.9 | 41204.9 | 2009-05-19 | 2011-06-30 | 2011-06-30 | 204 | C.M. FOREST PRODUCTS, INC. | 772
710380801 | 1 | MOORESTOWN MIX | 49 | 802.4 | 28338.05 | 28338.05 | 2009-05-19 | 2011-06-30 | 2011-06-30 | 204 | SHAWN MUMA LOGGING | 772
710470801 | 1 | BUZZONIA PINE | 7 | 85.2 | 1293.04 | 129.31 | 2009-04-28 | 2011-06-30 | 2011-06-30 | 204 | FRANK STUCKMAN | 793
710490801 | 1 | ROADSIDE ASPEN | 23 | 398.8 | 8977.39 | 897.74 | 2009-04-28 | 2011-06-30 | 2011-06-30 | 204 | SHAWN MUMA LOGGING | 793
710100901 | 1 | BEAVER RD. MIX | 130 | 2038.6 | 62600.26 | 40690.18 | 2009-05-19 | 2011-06-30 | 2011-06-30 | 204 | T. R. TIMBER COMPANY | 772
710130801 | 1 | UPSLOPE OAK | 41 | 533.2 | 10840.69 | 8163.98 | 2008-08-18 | 2010-09-30 | 2011-09-30 | 296 | DANKERT WOOD PRODUCTS | 1138
710220801 | 1 | OILFIELD ASPEN | 17 | 504.2 | 14958.83 | 14958.83 | 2008-10-06 | 2010-09-30 | 2011-09-30 | 296 | SHAWN MUMA LOGGING | 1089
710130901 | 1 | EAGER BEAVER ASPEN | 50 | 1193 | 34064.2 | 3406.42 | 2009-09-23 | 2011-09-30 | 2011-09-30 | 296 | C.M. FOREST PRODUCTS, INC. | 737
710170901 | 1 | MCGREGOR RP THIN | 72 | 502.3 | 29241.49 | 29241.49 | 2009-11-17 | 2011-12-31 | 2011-12-31 | 388 | HYDROLAKE, INC. | 774
710450801 | 1 | REEDSBURG MIX | 28 | 421.2 | 6012.5 | 601.25 | 2009-11-18 | 2011-12-31 | 2011-12-31 | 388 | BISBALLE FOREST PRODUCTS | 773
710040901 | 1 | TALL POLE PINE | 203 | 5905.5 | 481288.98 | 327276.5 | 2010-03-16 | 2012-03-31 | 2012-03-31 | 479 | LUTKE FOREST PRODUCTS, INC. | 746
710150901 | 1 | GRASS LAKE JACK | 48 | 713.6 | 20504.8 | 2050.48 | 2010-03-15 | 2012-03-31 | 2012-03-31 | 479 | C.M. FOREST PRODUCTS, INC. | 747
710200901 | 1 | MERIDIAN MIX | 194 | 2129 | 70530.5 | 20453.85 | 2010-04-12 | 2012-03-31 | 2012-03-31 | 479 | SHAWN MUMA LOGGING | 719
710051001 | 1 | TWIN LAKES OAK | 182 | 2787.8 | 118333.6 | 11833.36 | 2010-02-03 | 2012-03-31 | 2012-03-31 | 479 | T. R. TIMBER COMPANY | 787
710120901 | 1 | M-18 CROSSING | 89 | 503 | 12955.9 | 1295.59 | 2010-03-15 | 2012-03-31 | 2012-03-31 | 479 | C.M. FOREST PRODUCTS, INC. | 747
710310901 | 1 | LAST LINE ASPEN | 13 | 257.8 | 7850.8 | 7850.8 | 2010-03-15 | 2012-03-31 | 2012-03-31 | 479 | T. R. TIMBER COMPANY | 747
710320901 | 1 | EARLY ASPEN 1 | 54 | 898 | 23368.05 | 2336.81 | 2010-01-25 | 2012-03-31 | 2012-03-31 | 479 | C.M. FOREST PRODUCTS, INC. | 796
710300901 | 1 | WEST HIGGINS MIX | 80 | 1082.6 | 40221.71 | 4022.18 | 2010-03-15 | 2012-03-31 | 2012-03-31 | 479 | ROBERT OUTMAN | 747
710011001 | 1 | DECKERS VISTA | 11 | 273.6 | 6130.8 | 6130.8 | 2010-05-18 | 2012-06-30 | 2012-06-30 | 570 | C.M. FOREST PRODUCTS, INC. | 774
710350901 | 1 | CLOSE, YET FAR | 38 | 577.2 | 16685.1 | 16685.1 | 2010-04-27 | 2012-06-30 | 2012-06-30 | 570 | SHAWN MUMA LOGGING | 795
710061001 | 1 | NORTH KENO RED PINE | 41 | 560.4 | 44598.1 | 4459.81 | 2010-06-01 | 2012-06-30 | 2012-06-30 | 570 | JASON HELSEL | 760
710071001 | 1 | EARLY BIRD ASPEN | 78 | 2215 | 72103.85 | 7210.39 | 2010-07-08 | 2012-06-30 | 2012-06-30 | 570 | BISBALLE FOREST PRODUCTS | 723
710081001 | 1 | FIRESIDE HARVEST | 27 | 565.8 | 23773.05 | 2377.31 | 2010-06-29 | 2012-06-30 | 2012-06-30 | 570 | DIVERSIFIED FORESTRY | 732
710340901 | 1 | LONG WAY ASPEN | 47 | 1249.4 | 39293.9 | 18075.19 | 2010-05-04 | 2012-06-30 | 2012-06-30 | 570 | T. R. TIMBER COMPANY | 788
710091001 | 1 | EARLY ASPEN 2 | 116 | 3195 | 96590.45 | 9659.05 | 2010-05-18 | 2012-06-30 | 2012-06-30 | 570 | C.M. FOREST PRODUCTS, INC. | 774
710020901 | 1 | COTTAGE OAK | 97 | 1030 | 54807.58 | 5480.76 | 2010-05-04 | 2012-06-30 | 2012-06-30 | 570 | LEONARD FOREST PRODUCTS, INC. | 788
710110901 | 1 | F-97 DIVIDE | 160 | 1380.6 | 56407.25 | 5640.73 | 2010-05-06 | 2012-06-30 | 2012-06-30 | 570 | C.M. FOREST PRODUCTS, INC. | 786
710111001 | 1 | 4 CORNERS | 139 | 1921 | 65735.95 | 6573.6 | 2010-05-18 | 2012-06-30 | 2012-06-30 | 570 | C.M. FOREST PRODUCTS, INC. | 774
710021001 | 1 | NORTHEAST 37 | 25 | 297.4 | 5251.88 | 525.19 | 2010-06-28 | 2012-06-30 | 2012-06-30 | 570 | LEONARD FOREST PRODUCTS, INC. | 733
710010901 | 1 | MUSHROOM OAK | 29 | 402.4 | 14213.5 | 1421.35 | 2010-04-27 | 2012-06-30 | 2012-06-30 | 570 | SHAWN MUMA LOGGING | 795
710220901 | 1 | EXPERIMENTAL JACK | 43 | 427.6 | 13330.1 | 1333.01 | 2010-05-06 | 2012-06-30 | 2012-06-30 | 570 | C.M. FOREST PRODUCTS, INC. | 786
710230901 | 1 | MAYBEE OAK | 30 | 506.4 | 17550.75 | 17550.75 | 2010-05-11 | 2012-06-30 | 2012-06-30 | 570 | AJD FOR/PRO | 781
710250901 | 1 | BEARCLAW HARDWOODS | 27 | 231.6 | 10755.75 | 1075.58 | 2010-05-18 | 2012-06-30 | 2012-06-30 | 570 | DYERS SAWMILL | 774
710121001 | 1 | SPRING AHEAD ASPEN | 49 | 1056 | 30702 | 30702 | 2010-07-07 | 2012-06-30 | 2012-06-30 | 570 | SHAWN MUMA LOGGING | 724
710030901 | 1 | C166 OAK-ASPEN | 114 | 1983.6 | 79799.4 | 7979.94 | 2010-05-04 | 2012-06-30 | 2012-06-30 | 570 | T. R. TIMBER COMPANY | 788
710161001 | 1 | JUMPING JACK ASPEN | 47 | 665.8 | 17293.15 | 17293.15 | 2010-06-15 | 2012-06-30 | 2012-06-30 | 570 | SHAWN MUMA LOGGING | 746
710291001 | 1 | LAKESIDE MIX | 39 | 757.8 | 26253.51 | 2625.35 | 2010-10-05 | 2012-09-30 | 2012-09-30 | 662 | T. R. TIMBER COMPANY | 726
710031001 | 1 | MURRAY HILL OAK | 114 | 2091.8 | 81366.46 | 81366.46 | 2010-08-24 | 2012-09-30 | 2012-09-30 | 662 | SHAWN MUMA LOGGING | 768
710131001 | 1 | PATCH ASPEN | 22 | 564.6 | 20705.7 | 2070.57 | 2010-09-21 | 2012-09-30 | 2012-09-30 | 662 | C.M. FOREST PRODUCTS, INC. | 740
710311002 | 1 | POOR PINE REMOVAL | 13 | 170 | 1494 | 149.4 | 2010-07-21 | 2012-09-30 | 2012-09-30 | 662 | DANKERT WOOD PRODUCTS | 802
710251001 | 1 | PAULS ASPEN | 161 | 1363 | 39012 | 3901.2 | 2010-08-24 | 2012-09-30 | 2012-09-30 | 662 | SHAWN MUMA LOGGING | 768
710201001 | 1 | WET LINE ASPEN | 132 | 3156.2 | 107534.2 | 10753.42 | 2010-08-02 | 2012-09-30 | 2012-09-30 | 662 | SHAWN MUMA LOGGING | 790
710241001 | 1 | WILDFIRE ASPEN | 50 | 587 | 16290.45 | 1629.05 | 2010-08-24 | 2012-09-30 | 2012-09-30 | 662 | SHAWN MUMA LOGGING | 768
710231001 | 1 | HEADQUARTERS MIX | 91 | 1978.8 | 136479.25 | 76428.38 | 2010-08-02 | 2012-09-30 | 2012-09-30 | 662 | RON BUNDY | 790
710141001 | 1 | EAST ARTESIA ASPEN | 51 | 1129 | 36503.94 | 3650.39 | 2010-08-10 | 2012-09-30 | 2012-09-30 | 662 | T. R. TIMBER COMPANY | 782
710221001 | 1 | RIBBON RED PINE | 66 | 812.6 | 47875.3 | 25852.66 | 2010-09-07 | 2012-09-30 | 2012-09-30 | 662 | LEONARD FOREST PRODUCTS, INC. | 754
710101001 | 1 | COUNTY LINE COMPLEX | 91 | 1985.6 | 118647 | 118647 | 2010-10-05 | 2012-09-30 | 2012-09-30 | 662 | T. R. TIMBER COMPANY | 726
710041001 | 1 | SAGE LAKE OAK | 55 | 1035 | 54146.47 | 54146.47 | 2010-10-18 | 2012-12-31 | 2012-12-31 | 754 | TIM BILLS | 805
710171001 | 1 | CANOE CAMPS OAK | 44 | 426.6 | 15379.31 | 1537.93 | 2010-11-10 | 2012-12-31 | 2012-12-31 | 754 | DANKERT WOOD PRODUCTS | 782
710191001 | 1 | SAGE LAKE ASPEN | 56 | 1264.2 | 38343.45 | 38343.5 | 2010-10-14 | 2012-12-31 | 2012-12-31 | 754 | SHAWN MUMA LOGGING | 809
710301002 | 1 | M-18 REMOVAL | 9 | 75.4 | 1578 | 158 | 2010-10-26 | 2012-12-31 | 2012-12-31 | 754 | OMELL FOREST PRODUCTS | 797
710321001 | 1 | FAIRVIEW PINES | 195 | 3710 | 250760.06 | 25076.01 | 2010-10-26 | 2012-12-31 | 2012-12-31 | 754 | BIEWER SAWMILL, INC | 797
710351001 | 1 | BIG SCRAPE | 50 | 1561 | 132660.73 | 46432.15 | 2010-11-16 | 2012-12-31 | 2012-12-31 | 754 | SHAWN MUMA LOGGING | 776
710181001 | 1 | EXIT 222 | 52 | 392 | 18726.69 | 1872.67 | 2010-11-10 | 2012-12-31 | 2012-12-31 | 754 | BISBALLE FOREST PRODUCTS | 782